## Product Backlog
Item # | User Stories | Sprint # | Assigned To | Business Value | Story Points | PBI Type
1 | As a member, I want to view my current unpaid claims so that I can keep track of them | 1 | Software Developer 1 | 4 | 8 | Feature
2 | As a member, I want to view the details of a claim so that I have clarity | 1 | Software Developer 2 | 4 | 13 | Feature

## Sprint Backlog
Project | Theme | Epic | Sprint Goal | User Stories | Task(s) | Sub-Task(s) | Acceptance Criteria | Definition of Done | Dependencies | Estimation (Hrs)
Member portal of healthcare solution | Claims | Manage claims | Collaborate with stakeholders, including product owners and users, to create wireframes and mockups that illustrate the proposed UI design for managing unpaid claims. Consider usability best practices, visual hierarchy, and information architecture to ensure a user-friendly and intuitive interface. | As a member, I want to view my current unpaid claims so that I can keep track of them | 1. Create UI screen for showing results 2. Write business logic to get the value from DB 3. Review 4. Test cases 5. Validate the result | Sub-task for create UI for showing results of unpaid claims: 1. User Interface Design 2. Data Retrieval 3. Data Processing 4. Result Presentation | 1. Verify that only pending claims are listed. 2. Verify that claims are listed by dates 3. Verify that all claims of dependents are listed | For Acceptance Criteria 1: a. The code has been developed and reviewed, adhering to coding standards and best practices. b. Unit test have been written and executed successfully, ensuring the functionality works as expected. c. The feature has been tested manually to verify that only pending claims are displayed, while resolved and rejected claims not listed. | For Task 1: a. Backend/API integration b. Data availability and accuracy c. Claim processing logic (specific rules and calculations in determining unpaid claims) d. Design and prototyping e. User Interface Testing | For Task 1 8 hours

## Sprint Burndown Chart
Sprint Burndown Chart
Sprint Backlog ID | User Stories | Estimate (days) | 2007-08-01 | 2008-08-01 | 2009-08-01 | 2010-08-01 | 2011-08-01 | 2014-08-01 | 2015-08-01 | 2016-08-01 | 2017-08-01 | 2018-08-01
|  |  | 2007-08-01: Sprint 1; 2014-08-01: Sprint 2 | Remarks
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1x | Feature 1 | Day 0: 2; Sprint 1 Day 2: 1; Sprint 1 Day 4: 1
2x | Feature 2 | Day 0: 3; Sprint 1 Day 2: 2
3x | Feature 3 | 4 |  | 1 | 1 |  | -2 | 1 | 1 | 2 |  |  | Additional feature, extra work*
4x | Feature 4 | Day 0: 5; Sprint 1 Day 2: 1; Sprint 1 Day 4: 1; Sprint 2 Day 8: 1; Sprint 2 Day 9: 1; Sprint 2 Day 10: 1
5x | Feature 5 | Day 0: 6; Sprint 1 Day 2: 1; Sprint 1 Day 3: 1; Sprint 1 Day 5: 1; Sprint 2 Day 6: 1; Sprint 2 Day 7: 1
Remaining Effort |  | 20 | 20 | 14 | 12 | 10 | 11 | 9 | 7 | 4 | 3 | 2
Ideal Trend |  | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0